## Product Backlog
User Story
Sl # | As a | I want to | So that | Acceptance Criteria | Wireframe Reference
1 | Logged in Customer | upload a poor quality picture of my skin and press on submit button | I am redirected to the selfie capture page with an error message saying : "Your image is not valid. Take another image with better quality" | [give proper threshold values] 1. Blurry image should be rejected. 2. A low lighting image should be rejected. 3. A low resolution image should be rejected 4. A combination of any/all of the above three should be rejected 4. A proper image should not be rejected
2 | Logged in Customer | upload an acceptable quality picture of my skin and press on submit button | I can have my skin image analysed for visible skin concerns , be redirected to a questionnaire to give a complete profile of my skin, and finally view my reccomendations page with the following fields: 1. Hello "user_full_name" ! 2. Skin analysis results: Primary Concerns: those detected through the image. | 1. The user must only be allowed to proceed if the uploaded image passes all image-quality checks for blurriness, lighting, and resolution. 2. Once the image passes the quality checks, the image must be submitted to the Visual AI component for skin-concern analysis. 3. After successful Visual AI analysis, the user must be redirected to the skin questionnaire. 4. Detected skin concerns should be from the series: SC0001-SC0019 & SC1001-SC1009 5. If no skin concern is detected(perfectly fit skin) then Skin analysis results should show the following message: "Your skin looks perfect!" 6. If the image contains one or multiple particular skin concerns then, all of those should be shown in the Skin analysis results: Primary Concerns. 7. No other skins concerns should be shown in the Skin analysis results: Primary Concerns other than the ones really existing in the images and questionnaire.
3 | Logged in Customer | answer the provided questionnaire and press the submit button | I can view my reccomendation page with the following fields: 1. Hello "user_full_name"! 2. Skin analysis results : Primary Concerns : those detected through the combination of skin concerns from both image and questionnaire. 3.Skin analysis results: Skin Type: detected through questionnaire answers. 5. Reccomended for you: Base : selected through questionnaire answers. 6. Reccomended for you : Active Ingredients: those detected through selfie and questionnaire skin concerns. 7. Reccomended for you: Why this formula: explained by LLM for selected actives detected through selfie and questionnaire skin concerns | 1. Detected skin concerns should be from the series: SC0001-SC0019 , SC1001-SC1009 & SC2001-SC2004. 2. If no skin concern is detected(perfectly fit skin) then Skin analysis results should show the following message: "No skin concerns detected." 3.If the image & questionnaire contains one or multiple particular skin concerns then, all of those should be shown in the Skin analysis results: Primary Concerns. 4.No other skins concerns should be shown in the Skin analysis results: Primary Concerns other than the ones really existing in the images and questionnaire. 5. The total formulation must always weigh 100g total. 6. The percentage of actives in formulation must be listed. 7. The formulation explanation must correctly reflect the reason for choosing the actives and bases as per the LLM. 8. The actives and base comprising the reccomended formulation must be compatible with each other.
4 | Logged in Customer | press the add to cart button | I can add the reccomended formulation to my shopping cart . | 1.Upon add to cart button being clicked, the reccomended formulation should be saved for the user and added to their shopping cart, allowing them to buy later at their convenience. 2. The saved formulation in [1] must exactly match the reccomended formulation.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should all skin concerns be listed when we are only addressing top n.
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Get client verification

## Sprint Backlog
SPRINT BACKLOG
Sprint | User Story ID | Work Item | Tasks | T Shirt Sizing | Story Points | Team | Status | Blocker | Scope
1 | 1 | 1.1 | Receive image from Shopify widget | M | 3
Validate image file type
Validate image can be decoded/read
Validate image resolution
Calculate image sharpness
Calculate image brightness/lighting
Define/configure blur rejection threshold
Define/configure low-light rejection threshold
Define/configure minimum resolution threshold
|  | 1.2 | Combine all image-quality checks | M | 3
Reject image if any required quality check fails
Accept image only if all required checks pass
|  | 1.3 | Return image-validation result to frontend | XS
Display "Your image is not valid. Take another image with better quality"
Redirect user back to selfie capture
|  | 1.4 | Test invalid file type | L
Test unreadable image
Test low-resolution image
Test blurry image
Test low-light image
Test combinations of quality failures
Test valid image
Test User Story 1 acceptance criteria
| 2 | 2.1 | Redirect user to questionnaire after image passes validation checks. | XS
Store accepted image in skin_image
Associate image with current customer_session
|  | 2.2 | Define Visual AI response JSON schema based on image_detection.json | XS
Define supported image-detectable concern IDs: SC0001–SC0019, SC1001–SC1009
|  | 2.3 | Define Visual AI system prompt | XL |  | everyone
Define image-analysis instructions
Define skin-concern detection rules
Restrict output to supported concern IDs
Define no-concern behaviour
Require AI explanation for detected concerns
Require JSON-only response
|  | 2.4 | Send accepted image to Visual AI | L
Validate Visual AI response against JSON schema
Validate returned concern IDs
Handle duplicate concern IDs
Handle unsupported concern IDs
Handle empty/no-concern response
Handle malformed AI response
Handle AI/API failure
|  | 2.5 | Store Visual AI result in session_skin_concern_detection | S
Store detected concern IDs
Store AI-generated explanations
Store raw detection JSON
|  | 2.7 | Test Visual AI response validation | L
Test supported concern IDs
Test unsupported concern IDs
Test duplicate concern handling
Test multiple detected concerns
Test no visible concern
Test malformed AI response
Test AI/API failure
Test User Story 2 acceptance criteria
| 3 | 3.1 | Display questionnaire to user
Collect questionnaire answers
Validate required questionnaire fields
Store questionnaire answers in questionnaire_response
Associate questionnaire response with current customer_session
Submit questionnaire for LLM analysis
|  | 3.2 | Define questionnaire-analysis LLM prompt
Pass questionnaire JSON to LLM
Define concern extraction rules
Define skin-type extraction
Define sensitivity extraction
Define questionnaire-only concern handling
Validate LLM response
Handle malformed LLM response
Handle LLM/API failure
Store questionnaire detection result in session_skin_concern_detection
Store LLM-generated explanations
Store raw detection JSON
|  | 3.3 | Retrieve image-based detection results
Retrieve questionnaire-based detection results
Match results using skin_concern_id
Calculate image_skin_concern_exists OR questionnaire_skin_concern_exists
Combine image and questionnaire explanations
Store combined result in session_skin_concern
Handle concerns detected only from image
Handle concerns detected only from questionnaire
Handle concerns detected by both
Handle no detected concerns
Validate final combined concern set
|  | 3.4 | Retrieve combined skin concerns
Retrieve relevant concern_benefit mappings
Retrieve active_benefit_score data
Calculate/rank active candidates
Retrieve applicable bases using questionnaire/session information
Apply age suitability
Apply skin-type suitability
Apply climate/location considerations
Apply acne-suitability requirements
Apply questionnaire preferences
Check base-active compatibility
Produce candidate bases
Produce candidate actives
|  | 3.5 | Pass candidate information and relevant RAG information to LLM
Generate recommended base
Generate recommended active ingredients
Generate explanation for selected base
Generate explanation for selected actives
Ensure selected actives address detected concerns
Ensure selected actives are compatible with selected base
Generate formulation information
Validate recommendation output
|  | 3.6 | Create recommendation_run
Store selected base in recommendation_base
Store selected actives in recommendation_active
Store recommendation explanations
Store recommendation scores/ranks where applicable
Store final formatted response in recommendation_output
|  | 3.7 | Build final response containing user full name
Include combined primary skin concerns
Include skin type
Include sensitivity level
Include recommended base
Include recommended active ingredients
Include active percentages/quantities
Include formulation weight
Include formulation explanation
Include formulation/recommendation ID
Return recommendation response to Shopify widget
|  | 3.8 | Display user name
Display primary skin concerns
Display "Your skin looks perfect!" when no concern is detected
Display skin type
Display sensitivity level
Display recommended base
Display active ingredients
Display active percentages
Display formulation explanation
Display formulation information
|  | 3.9 | Handle no-compatible-recommendation case
Handle LLM failure
Handle database failure
Handle invalid recommendation/formulation
Return appropriate frontend error response
|  | 3.1 | Test questionnaire submission
Test questionnaire LLM analysis
Test concern fusion
Test image/questionnaire OR logic
Test candidate generation
Test base selection
Test active selection
Test base-active compatibility
Test formulation validation
Test 100 g formulation requirement
Test recommendation persistence
Test final recommendation response
Test no-concern scenario
Test recommendation error handling
Test User Story 3 acceptance criteria
| 4 | 4.1 | Identify required Shopify cart/API capability
Identify Shopify product/variant representing the formulation
Define formulation metadata required by Shopify cart
Create/test Shopify product or variant
|  | 4.2 | Receive formulation ID from frontend
Retrieve saved formulation
Verify formulation belongs to the logged-in customer/session
Verify formulation is valid
Add recommended formulation/product to Shopify cart
Attach required formulation metadata
Return cart response
|  | 4.3 | Implement Add to Cart button
Disable button while request is processing
Call Add to Cart API
Display successful cart-addition state
Handle Add to Cart failure
Prevent duplicate submissions
|  | 4.4 | Test formulation ID validation
Test customer/formulation ownership
Test Shopify cart item creation
Test formulation metadata
Test successful Add to Cart
Test Add to Cart failure
Test duplicate submission prevention
Test User Story 4 acceptance criteria
Note on H2: Author: TBD WiP Done
Note on C3: Author: Receive & Validate Image
Note on C12: Author: Image Quality Decision
Note on C15: Author: Rejection Flow
Note on C18: Author: Testing
Note on C26: Author: Image Session Storage
Note on C29: Author: Visual AI Output
Note on C31: Author: Visual AI Prompt
Note on C38: Author: Visual AI Integration
Note on C46: Author: Store Visual Analysis
Note on C50: Author: Testing
Note on C59: Author: Questionnaire Collection
Note on C65: Author: Questionnaire LLM Analysis
Note on C77: Author: Concern Fusion
Note on C88: Author: Candidate Generation
Note on C101: Author: Recommendation Generation
Note on C110: Author: Recommendation Persistence
Note on C116: Author: Final Recommendation Response
Note on C127: Author: Recommendation Screen
Note on C137: Author: Recommendation Error Handling
Note on C142: Author: Testing
Note on C157: Author: Shopify Cart Integration
Note on C161: Author: Add to Cart Backend
Note on C168: Author: Add to Cart UI
Note on C174: Author: Testing

## Updated Sprint
SPRINT BACKLOG
Sprint | User Story ID | Work Item | Tasks | T Shirt Sizing | Story Points | Team | Status | Blocker | Scope | Priority
1 | 1 | 1.1 | Receive image from Shopify widget and pass it to the image-validation service Validate uploaded image filetype before image processing Validate uploaded image can be decoded/read Validate image resolution against the configured minimum resolution. Calculate image sharpness score. Calculate image brightness/lighting score. Define/configure blur rejection threshold Define/configure low-light rejection threshold Define/configure minimum resolution threshold | L | 5 | Vidit | Done
|  | 1.2 | Combine all image-quality checks into one image-validation API call - POST /image-validation Reject image when any required quality check fails. Accept image only when all required quality checks pass. | M | 3 | Vidit | Done
|  | 1.3 | Return image-validation result to frontend Display "Your image is not valid. Take another image with better quality" Redirect user back to selfie capture | XS | 1 | Azad | Done
|  | 1.4 | Test invalid file type Test unreadable image Test low-resolution image Test blurry image Test low-light image Test combinations of quality failures Test valid image Test User Story 1 acceptance criteria | L | 5 | Everyone | Done
| 2 | 2.1 | Store accepted image in skin_image database table. Associate the stored image with the current customer_session database record using the session identifier. Trigger the asynchronous Visual AI image analysis process for the accepted image Redirect user to static questionnaire page immediately after image validation succeeds. | S | 2 | Vidit | Done
|  | 2.2 | Define Visual AI response JSON schema using image_detection.json as the schema definition. Define the skin_concern_id field in the Visual AI response. Restrict skin_concern_id values to SC0001–SC0019, SC1001–SC1009. | XS | 1 | Everyone | Done
|  | 2.3 | Define Visual AI system prompt Define image-analysis instructions Define skin-concern detection rules Restrict output to supported concern IDs Define no-concern behaviour Require AI explanation for every detected concerns Require JSON-only response | XL | 8 | everyone | WiP
|  | 2.4 | Send accepted image to Visual AI API for image analysis Validate Visual AI response against Visual AI response JSON schema Validate every returned skin_concern_id against the supported concern-ID list. Handle duplicate concern IDs before storing the results Handle unsupported concern IDs Handle empty/no-concern response Handle malformed AI response Handle AI/API failure | L | 5 | Sayan | Done
|  | 2.5 | Store the validated Visual AI result in session_skin_concern_detection database table Store the detected skin_concern_id value in the concern-ID column of session_skin_concern_detection. Store AI-generated explanations in the explanation column against the corresponding skin_concern_id. Store raw Visual AI response JSON in the raw-detection-JSON column Associate each detection record with the current customer_session. | S | 2 | Vidit | WiP
|  | 2.6 | Create the image analysis reccomendation response JSON. Populate user_full_name from the logged-in customer's user record. Populate Primary Concerns using only validated skin_concern_id values stored from the Visual AI analysis. Return "Your skin looks perfect!" when the validated image concern list is empty. Return the reccomendation response JSON to the Shopify widget frontend. Display user_full_name on the reccomendation page. Display image-detected Primary Concerns on the reccomendation page. | M | 3 | Azad, Sayan | WiP
|  | 2.7 | Test Visual AI response validation Test supported concern IDs Test unsupported concern IDs Test duplicate concern handling Test multiple detected concerns Test no visible concern Test malformed AI response Test AI/API failure Test asynchronous image analysis flow Test image-based recommendation response Test User Story 2 acceptance criteria | L | 5 | Everyone | TBD
|  | 2.8 | Generate 10–20 GenAI test images covering different skin tones, ages, and visible skin concerns Test redness detection across different skin tones Test redness detection on a person with black skin Test visible skin concerns on a person below 50 Test multiple visible skin concerns in a single image Test an image containing no visible skin concern Compare Visual AI returned skin_concern_id values against expected test results Verify unsupported concern IDs are not persisted in the session_skin_concern_detection database table | L | 5 | Everyone | TBD
|  |  | Total Sprint Story Points |  | 45
2 | 3 | 3.1 | Display questionnaire to user Collect questionnaire answers Validate required questionnaire fields Store questionnaire answers in questionnaire_response Associate questionnaire response with current customer_session Submit questionnaire for LLM analysis
|  | 3.2 | Define questionnaire-analysis LLM prompt Pass questionnaire JSON to LLM Define concern extraction rules Define skin-type extraction Define sensitivity extraction Define questionnaire-only concern handling
|  | 3.3 | Validate LLM response Handle malformed LLM response Handle LLM/API failure Store questionnaire detection result in session_skin_concern_detection Store LLM-generated explanations Store raw detection JSON
|  | 3.4 | Retrieve image-based detection results Retrieve questionnaire-based detection results Match results using skin_concern_id Calculate image_skin_concern_exists OR questionnaire_skin_concern_exists Combine image and questionnaire explanations Store combined result in session_skin_concern Handle concerns detected only from image Handle concerns detected only from questionnaire Handle concerns detected by both Handle no detected concerns Validate final combined concern set
|  | 3.5 | Retrieve combined skin concerns Retrieve relevant concern_benefit mappings Retrieve active_benefit_score data Retrieve applicable bases using questionnaire/session information Check base-active compatibility Produce candidate bases Produce candidate actives
|  | 3.6 | Pass candidate information , along with questionnaire answers to LLM Generate recommended base Generate recommended active ingredients Generate explanation for selected base Generate explanation for selected actives Ensure selected actives address detected concerns Ensure selected actives are compatible with selected base Generate formulation information
|  | 3.7 | Validate LLM recommendation output
|  | 3.8 | Create recommendation_run Store selected base in recommendation_base Store selected actives in recommendation_active Store recommendation explanations Store recommendation scores/ranks where applicable Store final formatted response in recommendation_output
|  | 3.9 | Build final response containing user full name Include combined primary skin concerns Include skin type Include sensitivity level Include recommended base Include recommended active ingredients Include active percentages/quantities Include formulation weight Include formulation explanation Include formulation/recommendation ID Return recommendation response to Shopify widget
|  | 3.1 | Display user name Display primary skin concerns Display "Your skin looks perfect!" when no concern is detected Display skin type Display sensitivity level Display recommended base Display active ingredients Display active percentages Display formulation explanation Display formulation information
|  | 3.11 | Handle no-compatible-recommendation case Handle LLM failure Handle database failure Handle invalid recommendation/formulation Return appropriate frontend error response
|  | 3.12 | Test questionnaire submission Test questionnaire LLM analysis Test concern fusion Test image/questionnaire OR logic Test candidate generation Test base selection Test active selection Test base-active compatibility Test formulation validation Test 100 g formulation requirement Test recommendation persistence Test final recommendation response Test no-concern scenario Test recommendation error handling Test User Story 3 acceptance criteria
| 4 | 4.1 | Identify required Shopify cart/API capability Identify Shopify product/variant representing the formulation Define formulation metadata required by Shopify cart Create/test Shopify product or variant
|  | 4.2 | Receive formulation ID from frontend Retrieve saved formulation Verify formulation belongs to the logged-in customer/session Verify formulation is valid Add recommended formulation/product to Shopify cart Attach required formulation metadata Return cart response
|  | 4.3 | Implement Add to Cart button Disable button while request is processing Call Add to Cart API Display successful cart-addition state Handle Add to Cart failure Prevent duplicate submissions
|  | 4.4 | Test formulation ID validation Test customer/formulation ownership Test Shopify cart item creation Test formulation metadata Test successful Add to Cart Test Add to Cart failure Test duplicate submission prevention Test User Story 4 acceptance criteria
Note on H2: Author: TBD WiP Done

## Burndown Chart
Days | Date | Actual Story Points Left | Excepted Story Points Left | Story Points Done
1 | 2026-08-31 | 45 | 45 | 1
2 | 2026-09-01 | 44 | 39.375 | 0
3 | 2026-09-02 | 39 | 33.75 | 5
4 | 2026-09-03 | 39 | 28.125 | 0
5 | 2026-09-04 | 36 | 22.5 | 3
6 | 2026-09-07 | 31 | 16.875 | 5
7 | 2026-09-08 | 31 | 11.25 | 0
8 | 2026-09-09 | 30 | 5.625 | 1
9 | 2026-09-10 | 30 | 0 | 0

## T Shirt sizing rules
TSHIRT SIZING
XS | S | M | L | XL | XXL | XXXL
1 | 2 | 3 | 5 | 8 | 13 | 21